## Gantt Chart
PROJECT GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | AI on low cost camera for counting and classification of microbes in nature water |  |  |  |  | PROJECT LEAD | [6 empty] | Artem Andrianov
PRODUCT OWNER |  | Dr. Antao Chen |  |  |  |  | DATE | [6 empty] | 2023-06-05
TASK NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | SPRINT 1 5/15 - 5/26 | [9 empty] | SPRINT 2 5/29 - 6/9 | [8 empty] | SPRINT 3 6/12 - 6/23 | [9 empty] | SPRINT 4 6/26 - 7/7 | [8 empty] | SPRINT 5 7/10 - 7/21
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  | WEEK 9 |  |  |  |  | WEEK 10
[7 empty] | M | T | W | T | F | M | T | W | T | F | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | R | F | M | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Obtain Hardware
1.1 | Determine camera based on previously existing projects | Mojeed | 2023-05-15 | 2023-05-26 | 11 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 6 T
1.2 | Purchase camera | Artem | 2023-05-15 | 2023-05-26 | 11 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 6 T
1.3 | Provide dimensions for microscope's camera mount | Artem | 2023-05-15 | 2023-05-26 | 11 | 100% | bar: WEEK 2 W to WEEK 2 T; WEEK 6 T
1.4 | Assist Professor with mounting camera | Artem | 2023-05-15 | 2023-05-26 | 11 | 100% | bar: WEEK 2 F; WEEK 6 T
1.5 | test camera quality on microscrope | Artem | 2023-05-15 | 2023-05-26 | 11 | 100% | bar: WEEK 2 F; WEEK 6 T
2 | Build Algae Dataset
2.1 | Find contacts at FIU/UM | Amanda | 2023-05-15 | 2023-05-19 | 5 | 100% | bar: WEEK 2 T to WEEK 3 F; WEEK 6 T
2.2 | Email researchers | Amanda | 2023-05-22 | 2023-05-29 | 5 | 100% | bar: WEEK 3 T to WEEK 3 F; WEEK 6 T
2.3 | Schedule meeting with researcher | Artem | 2023-06-05 | 2023-06-05 | 1 | 100% | bar: WEEK 4 M; WEEK 5 W; WEEK 6 T
2.4 | Take Pictures | Artem | 2023-06-08 | 2023-06-09 | 2 | 100% | bar: WEEK 4 T to WEEK 4 F; WEEK 6 T
2.5 | Process Pictures | Sam | 2023-06-09 | 2023-06-09 | 6 | 83% | bar: WEEK 4 F; WEEK 5 W to WEEK 6 T
2.6 | Generate additional pictures (rotate, flip, shear, etc) | Mojeed | 2023-06-08 | 2023-06-12 | 1 | 90% | bar: WEEK 5 M to WEEK 5 F; WEEK 6 T to WEEK 6 W
2.7 | Label dataset | Artem | 2023-06-13 | 2023-06-16 | 5 | 100% | bar: WEEK 4 F; WEEK 5 T to WEEK 5 F; WEEK 6 T to WEEK 6 W
3 | Build AI Model
3.1 | Determine programming languages | Sam | 2023-05-15 | 2023-05-26 | 10 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 6 T
3.2 | Determine libraries needed | Noah | 2023-05-15 | 2023-05-26 | 10 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 6 T
3.2.1 | Practice using libraries | Noah & Sam | 2023-06-06 | 2023-06-09 | 4 | 100% | bar: WEEK 4 T to WEEK 4 W; WEEK 5 M to WEEK 5 T; WEEK 6 T
3.2.2 | Build Keras Model using images | Noah | 2023-06-06 | 2023-06-13 | 6 | 55% | bar: WEEK 5 T; WEEK 6 M to WEEK 6 T; WEEK 6 T
3.3 | Optimize model in Keras | Sam | 2023-06-08 | 2023-06-15 | 6 | 0% | bar: WEEK 6 T
3.3.1 | Unit testing of model | Mojeed | 2023-06-15 | 2023-06-19 | 3 | 0% | bar: WEEK 6 T
4 | Port Model to Chip
4.1 | practice exporting model using TFLite | Artem | 2023-06-16 | 2023-06-23 | 6 | 40% | bar: WEEK 5 F to WEEK 6 T; WEEK 8 W
4.2 | Export Model to chip | Mojeed | 2023-06-13 | 2023-06-15 | 3 | 75% | bar: WEEK 6 T; WEEK 6 T to WEEK 9 F
4.3 | verify predictability of new data | Amanda | 2023-06-16 | 2023-06-19 | 2 | 0% | bar: WEEK 6 T
5 | Quality Improvements
5.1 | Optimize UI for ESP32 feed | Mojeed |  |  | 0 | 0% | bar: WEEK 6 T
5.2 | integrate object detection to model | Amanda | 2023-06-19 | 2023-06-28 | 9 | 35%
5.3 | Count algae in camera feed | Noah |  |  | 0 | 0% | bar: WEEK 6 T
5.4 | improve accuracy of model | Amanda |  |  | 0 | 0% | bar: WEEK 6 T
6 | Write up | Amanda
4.1 |  |  |  |  | 0 | 0% | bar: WEEK 6 T
4.2 |  |  |  |  | 0 | 0% | bar: WEEK 6 T
4.3 |  |  |  |  | 0 | 0% | bar: WEEK 6 T
4.4 |  |  |  |  | 0 | 0% | bar: WEEK 6 T